## Dashboard
Test Report Title : WorkSphere - ELMS
Test Report Provided by : Vaheeda Sheik
Module Name : Dashboard Page
Designation : QA Engineer
Date : 09/02/2026
Test Case ID | Test Description | Test Type | Priority | Severity | FR ID | UC ID | API Covered | DB Tables | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID
TC-HR-DASH-01 | Verify Total Employees card displays correct count | Functional | High | Major | FR-HR-DASH-01 | UC-HR-DASH-01 | GET /employees/count | employees | HR user logged in | Open HR dashboard | Correct total employee count shown
TC-HR-DASH-02 | Verify employee count updates on new employee addition | Integration | High | Major | FR-HR-DASH-01 | UC-HR-DASH-02 | GET /employees/count | employees | New employee added | Refresh dashboard | Count increases by 1
TC-HR-DASH-03 | Verify Attendance Today card count | Functional | High | Major | FR-HR-DASH-02 | UC-HR-DASH-03 | GET /attendance/today | attendance | Attendance marked | Open dashboard | Present/Total count correct
TC-HR-DASH-04 | Verify attendance percentage calculation | Functional | Medium | Minor | FR-HR-DASH-02 | UC-HR-DASH-04 | GET /attendance/today | attendance | Attendance data exists | Check % displayed | Percentage correctly calculated
TC-HR-DASH-05 | Verify Pending Leave Requests count | Functional | High | Major | FR-HR-DASH-03 | UC-HR-DASH-05 | GET /leaves/pending | leave_requests | Pending leaves exist | View card | Correct pending leave count
TC-HR-DASH-06 | Verify Payroll Processing amount | Functional | High | Critical | FR-HR-DASH-04 | UC-HR-DASH-06 | GET /payroll/summary | payroll | Payroll processed | Open dashboard | Correct payroll amount & month
TC-HR-DASH-07 | Verify Leave Request approval count | Functional | High | Major | FR-HR-DASH-05 | UC-HR-DASH-07 | GET /approvals/leaves | leave_requests | Pending leave approvals | View Pending Approvals | Correct count displayed
TC-HR-DASH-08 | Verify Attendance Regularization count | Functional | Medium | Major | FR-HR-DASH-05 | UC-HR-DASH-08 | GET /approvals/attendance | attendance | Regularization requests exist | View list | Correct count shown
TC-HR-DASH-09 | Verify New Employee Onboarding approvals | Functional | Medium | Major | FR-HR-DASH-05 | UC-HR-DASH-09 | GET /approvals/onboarding | employees | New hire pending | Open dashboard | Correct onboarding count
TC-HR-DASH-10 | Verify Policy Review approval count | Functional | Low | Minor | FR-HR-DASH-05 | UC-HR-DASH-10 | GET /approvals/policies | policies | Policies pending | View approvals | Count matches DB
TC-HR-DASH-11 | Verify clicking Review navigates to approval screen | Integration | High | Major | FR-HR-DASH-06 | UC-HR-DASH-11 | GET /approvals/{type} | multiple | HR logged in | Click Review | User navigated correctly
TC-HR-DASH-12 | Verify recent employee onboarding activity | Functional | Medium | Minor | FR-HR-DASH-07 | UC-HR-DASH-12 | GET /activities | audit_logs | New employee onboarded | View Recent Activity | Activity displayed
TC-HR-DASH-13 | Verify payroll processed activity | Functional | Medium | Minor | FR-HR-DASH-07 | UC-HR-DASH-13 | GET /activities | audit_logs | Payroll processed | Open dashboard | Payroll activity shown
TC-HR-DASH-14 | Verify activity timestamp accuracy | DB | Low | Minor | FR-HR-DASH-07 | UC-HR-DASH-14 | GET /activities | audit_logs | Activity exists | Check time shown | Timestamp correct
TC-HR-DASH-15 | Verify activities sorted by latest | Functional | Medium | Minor | FR-HR-DASH-07 | UC-HR-DASH-15 | GET /activities | audit_logs | Multiple activities | Observe order | Latest appears first
TC-HR-DASH-16 | Verify department-wise employee count | Functional | Medium | Major | FR-HR-DASH-08 | UC-HR-DASH-16 | GET /employees/department | employees | Employees assigned | View distribution | Correct count per dept
TC-HR-DASH-17 | Verify percentage calculation per department | Functional | Low | Minor | FR-HR-DASH-08 | UC-HR-DASH-17 | GET /employees/department | employees | Data exists | Check percentages | Correct percentages
TC-HR-DASH-18 | Verify bar length proportional to count | UI | Low | Minor | FR-HR-DASH-08 | UC-HR-DASH-18 | N/A | N/A | Dashboard loaded | Observe bars | Visual accuracy maintained
TC-HR-DASH-19 | Verify Add Employee quick action | Functional | High | Major | FR-HR-DASH-09 | UC-HR-DASH-19 | GET /employees/new | employees | HR logged in | Click Add Employee | Navigates to add employee page
TC-HR-DASH-20 | Verify Run Payroll quick action | Functional | High | Critical | FR-HR-DASH-09 | UC-HR-DASH-20 | POST /payroll/run | payroll | Payroll cycle open | Click Run Payroll | Payroll screen opens
TC-HR-DASH-21 | Verify View Attendance quick action | Functional | Medium | Major | FR-HR-DASH-09 | UC-HR-DASH-21 | GET /attendance | attendance | Attendance data exists | Click View Attendance | Attendance page opens
TC-HR-DASH-22 | Verify Manage Policies quick action | Functional | Medium | Major | FR-HR-DASH-09 | UC-HR-DASH-22 | GET /policies | policies | HR logged in | Click Manage Policies | Policy management page opens
TC-HR-DASH-23 | Verify non-HR user cannot access HR dashboard | Security | High | Critical | FR-HR-DASH-10 | UC-HR-DASH-23 | GET /hr/dashboard | roles | Logged in as Employee | Access HR dashboard URL | Access denied
TC-HR-DASH-24 | Verify only HR can run payroll | Security | High | Critical | FR-HR-DASH-10 | UC-HR-DASH-24 | POST /payroll/run | roles | Logged in as non-HR | Click Run Payroll | Action restricted
TC-HR-DASH-25 | Verify approval actions restricted to HR | Security | High | Critical | FR-HR-DASH-10 | UC-HR-DASH-25 | POST /approvals | roles | Logged in as Manager | Attempt approval | Permission denied

## Employee
Test Report Title : WorkSphere - ELMS
Test Report Provided by : Vaheeda Sheik
Module Name : Employee Management
Designation : QA Engineer
Date : 09/02/2026
Test Case ID | Test Description | Test Type | Priority | Severity | FR-HR ID | UC-HR ID | API Covered | DB Tables | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID
TC-HR-EMP-01 | Verify Add Employee button visibility for HR/Admin | Functional | High | Major | FR-HR-EMP-01 | UC-HR-EMP-01 | GET /employees | employees | HR/Admin logged in | Open Employee Management page | Add Employee button is visible
TC-HR-EMP-02 | Verify Add Employee button hidden for normal employee | Security | High | Critical | FR-HR-EMP-01 | UC-HR-EMP-02 | GET /employees | employees | Employee logged in | Open Employee Management page | Add Employee button not visible
TC-HR-EMP-03 | Verify Add Employee button navigation | Functional | High | Major | FR-HR-EMP-02 | UC-HR-EMP-03 | GET /employees/new | employees | HR/Admin logged in | Click Add Employee | Add Employee form opens
TC-HR-EMP-04 | Verify search by employee name | Functional | High | Major | FR-HR-EMP-03 | UC-HR-EMP-04 | GET /employees?search= | employees | Employee records exist | Enter valid employee name | Matching employees displayed
TC-HR-EMP-05 | Verify search by employee ID | Functional | Medium | Major | FR-HR-EMP-03 | UC-HR-EMP-04 | GET /employees?search= | employees | Employee records exist | Enter employee ID | Correct employee shown
TC-HR-EMP-06 | Verify search with no results | Negative | Medium | Minor | FR-HR-EMP-03 | UC-HR-EMP-05 | GET /employees?search= | employees | Employee records exist | Enter invalid keyword | “No records found” message
TC-HR-EMP-07 | Verify department dropdown values | Functional | Medium | Minor | FR-HR-EMP-04 | UC-HR-EMP-06 | GET /departments | departments | Departments configured | Open department dropdown | All departments listed
TC-HR-EMP-08 | Verify filter by department | Functional | High | Major | FR-HR-EMP-04 | UC-HR-EMP-07 | GET /employees?department= | employees | Employees mapped to departments | Select department | Employees filtered correctly
TC-HR-EMP-09 | Verify status dropdown values | Functional | Medium | Minor | FR-HR-EMP-05 | UC-HR-EMP-08 | GET /employees/status | employees | Status configured | Open status dropdown | Active/Inactive shown
TC-HR-EMP-10 | Verify filter by Active status | Functional | High | Major | FR-HR-EMP-05 | UC-HR-EMP-09 | GET /employees?status=Active | employees | Active employees exist | Select Active status | Only active employees shown
TC-HR-EMP-11 | Verify filter by Inactive status | Functional | Medium | Major | FR-HR-EMP-05 | UC-HR-EMP-10 | GET /employees?status=Inactive | employees | Inactive employees exist | Select Inactive status | Only inactive employees shown
TC-HR-EMP-12 | Verify status column displays correct value | Functional | High | Major | FR-HR-EMP-06 | UC-HR-EMP-11 | GET /employees | employees | Employee list available | Observe status column | Correct status shown
TC-HR-EMP-13 | Verify View button is visible for each employee | UI | Medium | Minor | FR-HR-EMP-07 | UC-HR-EMP-12 | — | — | Employee listed | Observe View button | View button displayed
TC-HR-EMP-14 | Verify View button navigates to Employee Details page | Functional | High | Major | FR-HR-EMP-07 | UC-HR-EMP-13 | GET /employees/{id} | employees | Employee exists | Click View | Employee details page opens
TC-HR-EMP-15 | Verify employee details displayed correctly | Functional | High | Major | FR-HR-EMP-07 | UC-HR-EMP-14 | GET /employees/{id} | employees | Details page opened | Verify data | Details match DB records
TC-HR-EMP-16 | Verify unauthorized user cannot access employee details | Security | High | Critical | FR-HR-EMP-07 | UC-HR-EMP-15 | GET /employees/{id} | roles | Employee logged in | Access URL | Access denied
TC-HR-EMP-17 | Verify Edit button visible on Employee Details page | UI | Medium | Minor | FR-HR-EMP-08 | UC-HR-EMP-16 | — | — | Details page open | Observe Edit button | Edit button visible
TC-HR-EMP-18 | Verify Edit button navigates to Employee Profile page | Functional | High | Major | FR-HR-EMP-08 | UC-HR-EMP-17 | GET /employees/{id}/edit | employees | HR logged in | Click Edit | Edit profile page opens
TC-HR-EMP-19 | Verify employee details are editable | Functional | High | Major | FR-HR-EMP-08 | UC-HR-EMP-18 | PUT /employees/{id} | employees | Edit page open | Modify fields & save | Changes saved successfully
TC-HR-EMP-20 | Verify updated data reflected in employee list | Integration | Medium | Major | FR-HR-EMP-08 | UC-HR-EMP-19 | GET /employees | employees | Employee updated | Navigate to list | Updated data displayed
TC-HR-EMP-21 | Verify non-HR cannot edit employee profile | Security | High | Critical | FR-HR-EMP-08 | UC-HR-EMP-20 | PUT /employees/{id} | roles | Employee logged in | Attempt edit | Access denied
TC-HR-EMP-22 | Verify Delete button visible for HR | UI | Medium | Minor | FR-HR-EMP-09 | UC-HR-EMP-21 | — | — | HR logged in | Observe Delete button | Delete button visible
TC-HR-EMP-23 | Verify delete confirmation popup | Functional | High | Major | FR-HR-EMP-09 | UC-HR-EMP-22 | DELETE /employees/{id} | employees | Employee exists | Click Delete | Confirmation popup shown
TC-HR-EMP-24 | Verify employee deleted successfully | Functional | High | Critical | FR-HR-EMP-09 | UC-HR-EMP-23 | DELETE /employees/{id} | employees | Confirm delete | Employee removed from list
TC-HR-EMP-25 | Verify deleted employee not present in DB | DB | High | Critical | FR-HR-EMP-09 | UC-HR-EMP-24 | DELETE /employees/{id} | employees | Employee deleted | Verify DB | Record removed / deactivated
TC-HR-EMP-26 | Verify cancel delete action | Negative | Medium | Minor | FR-HR-EMP-09 | UC-HR-EMP-25 | — | — | Confirmation popup shown | Click Cancel | Employee not deleted
TC-HR-EMP-27 | Verify delete action logged in audit | Audit | Medium | Minor | FR-HR-EMP-09 | UC-HR-EMP-26 | DELETE /employees/{id} | audit_logs | Employee deleted | Check audit log | Delete action logged
TC-HR-EMP-28 | Verify pagination appears when record limit exceeded | Functional | Medium | Minor | FR-HR-EMP-10 | UC-HR-EMP-27 | GET /employees?page= | employees | More than page limit records | Open employee list | Pagination visible
TC-HR-EMP-29 | Verify pagination navigation | Functional | Medium | Minor | FR-HR-EMP-10 | UC-HR-EMP-28 | GET /employees?page=2 | employees | Multiple pages exist | Click Next page | Next page records shown
TC-HR-EMP-30 | Verify pagination retains applied filters | Integration | Medium | Major | FR-HR-EMP-10 | UC-HR-EMP-29 | GET /employees?page=&filter= | employees | Filter applied | Navigate pages | Filter remains applied
TC-HR-EMP-31 | Verify pagination resets after changing filter | Functional | Low | Minor | FR-HR-EMP-10 | UC-HR-EMP-30 | GET /employees | employees | On page >1 | Change filter | Page resets to first page
TC-HR-EMP-32 | Verify handling of invalid employee ID | Negative | High | Major | FR-HR-EMP-11 | UC-HR-EMP-31 | GET /employees/{id} | — | Invalid ID | Access details page | Proper error message
TC-HR-EMP-33 | Verify system behavior when delete API fails | Negative | High | Major | FR-HR-EMP-11 | UC-HR-EMP-32 | DELETE /employees/{id} | — | API down | Delete employee | Error message shown
TC-HR-EMP-ONB-01 | Verify Create New Employee form loads successfully | Functional | High | Major | FR-HR-EMP-12 | UC-HR-EMP-33 | GET /employees/new | employees | HR/Admin logged in | Open Create Employee page | Form loads with all mandatory fields
TC-HR-EMP-ONB-02 | Verify all mandatory fields are marked with * | UI | Medium | Minor | FR-HR-EMP-12 | UC-HR-EMP-34 | — | — | Form opened | Observe field labels | Mandatory fields clearly marked
TC-HR-EMP-ONB-03 | Verify Employee ID accepts valid format | Functional | High | Major | FR-HR-EMP-13 | UC-HR-EMP-35 | POST /employees | employees | HR/Admin logged in | Enter valid Employee ID | Employee ID accepted
TC-HR-EMP-ONB-04 | Verify Employee ID uniqueness | Integration | High | Critical | FR-HR-EMP-13 | UC-HR-EMP-36 | POST /employees | employees | Employee ID already exists | Enter duplicate ID and submit | Error message displayed
TC-HR-EMP-ONB-05 | Verify Employee ID mandatory validation | Negative | High | Major | FR-HR-EMP-13 | UC-HR-EMP-37 | POST /employees | employees | Form opened | Leave Employee ID blank | Validation error shown
TC-HR-EMP-ONB-06 | Verify Name accepts alphabetic characters | Functional | Medium | Minor | FR-HR-EMP-14 | UC-HR-EMP-38 | POST /employees | employees | Form opened | Enter valid name | Name accepted
TC-HR-EMP-ONB-07 | Verify Name mandatory validation | Negative | High | Major | FR-HR-EMP-14 | UC-HR-EMP-39 | POST /employees | employees | Form opened | Leave Name blank | Validation error shown
TC-HR-EMP-ONB-08 | Verify Name rejects numeric values | Negative | Medium | Minor | FR-HR-EMP-14 | UC-HR-EMP-40 | POST /employees | employees | Form opened | Enter numeric characters | Validation error shown
TC-HR-EMP-ONB-09 | Verify Email accepts valid format | Functional | High | Major | FR-HR-EMP-15 | UC-HR-EMP-41 | POST /employees | employees | Form opened | Enter valid email | Email accepted
TC-HR-EMP-ONB-10 | Verify Email rejects invalid format | Negative | High | Major | FR-HR-EMP-15 | UC-HR-EMP-42 | POST /employees | employees | Form opened | Enter invalid email | Validation error shown
TC-HR-EMP-ONB-11 | Verify Email uniqueness validation | Integration | High | Critical | FR-HR-EMP-15 | UC-HR-EMP-43 | POST /employees | employees | Email already exists | Submit duplicate email | Error message displayed
TC-HR-EMP-ONB-12 | Verify Phone Number accepts valid digits | Functional | Medium | Minor | FR-HR-EMP-16 | UC-HR-EMP-44 | POST /employees | employees | Form opened | Enter valid phone number | Phone number accepted
TC-HR-EMP-ONB-13 | Verify Phone Number length validation | Negative | Medium | Minor | FR-HR-EMP-16 | UC-HR-EMP-45 | POST /employees | employees | Form opened | Enter invalid length number | Validation error shown
TC-HR-EMP-ONB-14 | Verify Phone Number mandatory validation | Negative | High | Major | FR-HR-EMP-16 | UC-HR-EMP-46 | POST /employees | employees | Form opened | Leave Phone Number blank | Validation error shown
TC-HR-EMP-ONB-15 | Verify Department dropdown values | Functional | Medium | Minor | FR-HR-EMP-17 | UC-HR-EMP-47 | GET /departments | departments | Departments configured | Open Department dropdown | All departments listed
TC-HR-EMP-ONB-16 | Verify Designation dropdown values | Functional | Medium | Minor | FR-HR-EMP-18 | UC-HR-EMP-48 | GET /designations | designations | Designations configured | Open Designation dropdown | All designations listed
TC-HR-EMP-ONB-17 | Verify Role dropdown values | Security | High | Major | FR-HR-EMP-19 | UC-HR-EMP-49 | GET /roles | roles | Roles configured | Open Role dropdown | Valid roles listed
TC-HR-EMP-ONB-18 | Verify Department mandatory validation | Negative | High | Major | FR-HR-EMP-17 | UC-HR-EMP-50 | POST /employees | employees | Form opened | Do not select Department | Validation error shown
TC-HR-EMP-ONB-19 | Verify Join Date accepts valid date | Functional | Medium | Minor | FR-HR-EMP-20 | UC-HR-EMP-51 | POST /employees | employees | Form opened | Select valid Join Date | Date accepted
TC-HR-EMP-ONB-20 | Verify future Join Date validation | Negative | Medium | Minor | FR-HR-EMP-20 | UC-HR-EMP-52 | POST /employees | employees | Form opened | Select future date | Validation error shown
TC-HR-EMP-ONB-21 | Verify Monthly Salary accepts numeric value | Functional | High | Major | FR-HR-EMP-21 | UC-HR-EMP-53 | POST /employees | employees | Form opened | Enter valid salary | Salary accepted
TC-HR-EMP-ONB-22 | Verify Monthly Salary mandatory validation | Negative | High | Major | FR-HR-EMP-21 | UC-HR-EMP-54 | POST /employees | employees | Form opened | Leave salary blank | Validation error shown
TC-HR-EMP-ONB-23 | Verify Reporting Manager dropdown values | Functional | Medium | Minor | FR-HR-EMP-22 | UC-HR-EMP-55 | GET /employees/managers | employees | Managers exist | Open Reporting Manager dropdown | Managers listed
TC-HR-EMP-ONB-24 | Verify Create Employee button creates employee | Functional | High | Major | FR-HR-EMP-23 | UC-HR-EMP-56 | POST /employees | employees | All mandatory fields filled | Click Submit | Employee created successfully
TC-HR-EMP-ONB-25 | Verify employee record saved in DB | DB | High | Critical | FR-HR-EMP-23 | UC-HR-EMP-57 | POST /employees | employees | Employee created | Verify DB entry | Record saved correctly
TC-HR-EMP-ONB-26 | Verify Cancel button navigates to employee list | Functional | Medium | Minor | FR-HR-EMP-24 | UC-HR-EMP-58 | — | — | Form opened | Click Cancel | Redirected to Employee list
TC-HR-EMP-ONB-27 | Verify Cancel does not save data | Negative | Medium | Minor | FR-HR-EMP-24 | UC-HR-EMP-59 | — | employees | Form partially filled | Click Cancel | No record saved
TC-HR-EMP-ONB-28 | Verify non-HR user cannot access Create Employee page | Security | High | Critical | FR-HR-EMP-25 | UC-HR-EMP-60 | GET /employees/new | roles | Employee logged in | Access Create Employee URL | Access denied

## Attendance
Test Report Title : WorkSphere - ELMS
Test Report Provided by : Vaheeda Sheik
Module Name : HR-ATTendance Management Page
Designation : QA Engineer
Date : 09/02/2026
Test Case ID | Test Description | Test Type | Priority | Severity | FR ID | UC ID | API Covered | DB Tables | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID
TC-HR-ATT-01 | Verify Attendance page loads successfully | Functional | High | Major | FR-HR-ATT-01 | UC-HR-ATT-01 | GET /attendance | attendance | Employee logged in | Open Attendance page | Attendance page loads successfully
TC-HR-ATT-02 | Verify Present Today card count | Functional | High | Major | FR-HR-ATT-02 | UC-HR-ATT-02 | GET /attendance/summary | attendance | Attendance data exists | View Present Today card | Correct present count displayed
TC-HR-ATT-03 | Verify Absent Today card count | Functional | High | Major | FR-HR-ATT-02 | UC-HR-ATT-03 | GET /attendance/summary | attendance | Attendance data exists | View Absent Today card | Correct absent count displayed
TC-HR-ATT-04 | Verify On Leave card count | Functional | High | Major | FR-HR-ATT-02 | UC-HR-ATT-04 | GET /attendance/summary | leave_requests | Leave data exists | View On Leave card | Correct leave count displayed
TC-HR-ATT-05 | Verify Total Employees card count | Functional | Medium | Minor | FR-HR-ATT-02 | UC-HR-ATT-05 | GET /employees/count | employees | Employees exist | View Total Employees card | Correct employee count shown
TC-HR-ATT-06 | Verify calendar is displayed on Attendance page | Functional | Medium | Minor | FR-HR-ATT-03 | UC-HR-ATT-06 | — | — | Attendance page loaded | Observe calendar | Calendar displayed
TC-HR-ATT-07 | Verify current date is highlighted in calendar | Functional | High | Major | FR-HR-ATT-03 | UC-HR-ATT-07 | — | — | Attendance page loaded | Check today’s date | Current date highlighted
TC-HR-ATT-08 | Verify navigation between months in calendar | Functional | Medium | Minor | FR-HR-ATT-03 | UC-HR-ATT-08 | — | — | Calendar visible | Navigate to previous/next month | Calendar navigates correctly
TC-HR-ATT-09 | Verify selecting a date filters attendance data | Integration | High | Major | FR-HR-ATT-03 | UC-HR-ATT-09 | GET /attendance?date= | attendance | Attendance data exists | Select a date | Records updated for selected date
TC-HR-ATT-10 | Verify On Leave employee list displayed | Functional | High | Major | FR-HR-ATT-04 | UC-HR-ATT-10 | GET /leave/on-leave | leave_requests | Leave records exist | View On Leave section | Employee list displayed
TC-HR-ATT-11 | Verify leave date range shown correctly | Functional | Medium | Minor | FR-HR-ATT-04 | UC-HR-ATT-11 | GET /leave/on-leave | leave_requests | Leave records exist | Verify leave dates | Correct date range shown
TC-HR-ATT-12 | Verify leave type displayed correctly | Functional | Medium | Minor | FR-HR-ATT-04 | UC-HR-ATT-12 | GET /leave/on-leave | leave_types | Leave records exist | Check leave type | Correct leave type displayed
TC-HR-ATT-13 | Verify search by employee name | Functional | High | Major | FR-HR-ATT-05 | UC-HR-ATT-13 | GET /attendance?search= | attendance | Attendance records exist | Enter employee name | Matching records displayed
TC-HR-ATT-14 | Verify filter by department | Functional | Medium | Minor | FR-HR-ATT-05 | UC-HR-ATT-14 | GET /attendance?department= | departments | Departments exist | Select department | Records filtered correctly
TC-HR-ATT-15 | Verify filter by attendance status | Functional | Medium | Minor | FR-HR-ATT-05 | UC-HR-ATT-15 | GET /attendance?status= | attendance | Attendance records exist | Select status | Records filtered correctly
TC-HR-ATT-16 | Verify combined filters work correctly | Integration | High | Major | FR-HR-ATT-05 | UC-HR-ATT-16 | GET /attendance | attendance | Records exist | Apply multiple filters | Correct filtered results
TC-HR-ATT-17 | Verify attendance records list displayed | Functional | High | Major | FR-HR-ATT-06 | UC-HR-ATT-17 | GET /attendance/records | attendance | Attendance records exist | View records table | Records displayed
TC-HR-ATT-18 | Verify check-in time displayed correctly | Functional | Medium | Minor | FR-HR-ATT-06 | UC-HR-ATT-18 | GET /attendance/records | attendance | Records exist | Check check-in time | Correct time displayed
TC-HR-ATT-19 | Verify check-out time displayed correctly | Functional | Medium | Minor | FR-HR-ATT-06 | UC-HR-ATT-19 | GET /attendance/records | attendance | Records exist | Check check-out time | Correct time displayed
TC-HR-ATT-20 | Verify attendance status displayed (Present/Late/Absent) | Functional | High | Major | FR-HR-ATT-06 | UC-HR-ATT-20 | GET /attendance/records | attendance | Records exist | Check status column | Correct status displayed
TC-HR-ATT-21 | Verify Export Report button visible | UI | Medium | Minor | FR-HR-ATT-07 | UC-HR-ATT-21 | — | — | Attendance page loaded | Observe Export button | Export button visible
TC-HR-ATT-22 | Verify export report for selected date | Functional | High | Major | FR-HR-ATT-07 | UC-HR-ATT-22 | GET /attendance/export | attendance | Records exist | Select date and export | Report downloaded successfully
TC-HR-ATT-23 | Verify exported report data accuracy | DB | High | Critical | FR-HR-ATT-07 | UC-HR-ATT-23 | GET /attendance/export | attendance | Report downloaded | Compare with DB | Data matches DB
TC-HR-ATT-24 | Verify employee cannot edit attendance records | Security | High | Critical | FR-HR-ATT-08 | UC-HR-ATT-24 | PUT /attendance | roles | Employee logged in | Attempt edit | Access denied
TC-HR-ATT-25 | Verify unauthorized user cannot access attendance page | Security | High | Critical | FR-HR-ATT-08 | UC-HR-ATT-25 | GET /attendance | roles | Not logged in | Access URL directly | Redirect to login

## Payroll
Test Report Title : WorkSphere - ELMS
Test Report Provided by : Vaheeda Sheik
Module Name : HR-PAYroll Management Page
Designation : QA Engineer
Date : 09/02/2026
Test Case ID | Test Description | Test Type | Priority | Severity | FR ID | UC ID | API Covered | DB Tables | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID
TC-HR-PAY-01 | Verify Payroll Management page loads successfully | Functional | High | Major | FR-HR-PAY-01 | UC-HR-PAY-01 | GET /payroll | payroll | HR/Admin logged in | Open Payroll Management page | Page loads successfully
TC-HR-PAY-02 | Verify Total Payroll card value | Functional | High | Major | FR-HR-PAY-02 | UC-HR-PAY-02 | GET /payroll/summary | payroll | Payroll data exists | View Total Payroll card | Correct total payroll displayed
TC-HR-PAY-03 | Verify Employees card count | Functional | Medium | Minor | FR-HR-PAY-02 | UC-HR-PAY-03 | GET /employees/count | employees | Employees exist | View Employees card | Correct employee count shown
TC-HR-PAY-04 | Verify Average Salary card value | Functional | Medium | Minor | FR-HR-PAY-02 | UC-HR-PAY-04 | GET /payroll/summary | payroll | Payroll data exists | View Average Salary card | Correct average salary shown
TC-HR-PAY-05 | Verify Payslips Uploaded card count | Functional | Medium | Minor | FR-HR-PAY-02 | UC-HR-PAY-05 | GET /payslips/count | payslips | Payslips exist | View Payslips Uploaded card | Correct count displayed
TC-HR-PAY-06 | Verify Run Payroll button visibility | UI | Medium | Minor | FR-HR-PAY-03 | UC-HR-PAY-06 | — | — | Payroll page loaded | Observe Run Payroll button | Button visible
TC-HR-PAY-07 | Verify navigation to Run Payroll page | Functional | High | Major | FR-HR-PAY-03 | UC-HR-PAY-07 | GET /payroll/run | payroll | HR/Admin logged in | Click Run Payroll | Run Payroll page displayed
TC-HR-PAY-08 | Verify Total Employees displayed in Run Payroll page | Functional | High | Major | FR-HR-PAY-04 | UC-HR-PAY-08 | GET /employees/count | employees | Employees exist | View Total Employees | Correct count displayed
TC-HR-PAY-09 | Verify Estimated Total Payroll amount | Functional | High | Major | FR-HR-PAY-04 | UC-HR-PAY-09 | GET /payroll/estimate | payroll | Salary data exists | View estimated amount | Correct payroll amount shown
TC-HR-PAY-10 | Verify Processing Date default value | Functional | Medium | Minor | FR-HR-PAY-04 | UC-HR-PAY-10 | — | — | Run Payroll page loaded | Check processing date | Current date selected by default
TC-HR-PAY-11 | Verify Cancel button navigation | Functional | Medium | Minor | FR-HR-PAY-05 | UC-HR-PAY-11 | — | — | Run Payroll page opened | Click Cancel | Redirected to Payroll page
TC-HR-PAY-12 | Verify Run Payroll button processes payroll | Functional | High | Critical | FR-HR-PAY-05 | UC-HR-PAY-12 | POST /payroll/run | payroll | All data valid | Click Run Payroll | Payroll processed successfully
TC-HR-PAY-13 | Verify payroll records created in DB | DB | High | Critical | FR-HR-PAY-05 | UC-HR-PAY-13 | POST /payroll/run | payroll | Payroll processed | Verify DB records | Records saved correctly
TC-HR-PAY-14 | Verify search by employee name | Functional | High | Major | FR-HR-PAY-06 | UC-HR-PAY-14 | GET /payroll?search= | payroll | Payroll records exist | Enter employee name | Matching records displayed
TC-HR-PAY-15 | Verify filter by month dropdown | Functional | Medium | Minor | FR-HR-PAY-06 | UC-HR-PAY-15 | GET /payroll?month= | payroll | Records exist | Select month | Records filtered correctly
TC-HR-PAY-16 | Verify filter by year dropdown | Functional | Medium | Minor | FR-HR-PAY-06 | UC-HR-PAY-16 | GET /payroll?year= | payroll | Records exist | Select year | Records filtered correctly
TC-HR-PAY-17 | Verify combined filters functionality | Integration | High | Major | FR-HR-PAY-06 | UC-HR-PAY-17 | GET /payroll | payroll | Records exist | Apply multiple filters | Correct filtered results
TC-HR-PAY-18 | Verify payroll records list displayed | Functional | High | Major | FR-HR-PAY-07 | UC-HR-PAY-18 | GET /payroll/records | payroll | Payroll records exist | View records table | Records displayed
TC-HR-PAY-19 | Verify month and year displayed correctly | Functional | Medium | Minor | FR-HR-PAY-07 | UC-HR-PAY-19 | GET /payroll/records | payroll | Records exist | Check month/year | Correct values displayed
TC-HR-PAY-20 | Verify net amount displayed correctly | Functional | High | Major | FR-HR-PAY-07 | UC-HR-PAY-20 | GET /payroll/records | payroll | Records exist | Check net amount | Correct amount displayed
TC-HR-PAY-21 | Verify payroll status displayed | Functional | Medium | Minor | FR-HR-PAY-07 | UC-HR-PAY-21 | GET /payroll/records | payroll | Records exist | Check status column | Correct status shown
TC-HR-PAY-22 | Verify Upload button visible for non-uploaded payslip | Functional | Medium | Minor | FR-HR-PAY-08 | UC-HR-PAY-22 | POST /payslips/upload | payslips | Payslip not uploaded | View Upload button | Upload button visible
TC-HR-PAY-23 | Verify payslip upload functionality | Functional | High | Critical | FR-HR-PAY-08 | UC-HR-PAY-23 | POST /payslips/upload | payslips | Valid file available | Upload payslip | Payslip uploaded successfully
TC-HR-PAY-24 | Verify Upload button replaced with Uploaded status | Functional | Medium | Minor | FR-HR-PAY-08 | UC-HR-PAY-24 | GET /payslips | payslips | Payslip uploaded | Refresh page | Status updated to Uploaded
TC-HR-PAY-25 | Verify Download payslip button | Functional | High | Major | FR-HR-PAY-09 | UC-HR-PAY-25 | GET /payslips/download | payslips | Payslip uploaded | Click Download | Payslip downloaded
TC-HR-PAY-26 | Verify pagination displayed | UI | Medium | Minor | FR-HR-PAY-10 | UC-HR-PAY-26 | — | — | Records exceed page limit | Scroll to bottom | Pagination visible
TC-HR-PAY-27 | Verify pagination navigation | Functional | Medium | Minor | FR-HR-PAY-10 | UC-HR-PAY-27 | GET /payroll?page= | payroll | Multiple pages exist | Navigate pages | Correct records displayed
TC-HR-PAY-28 | Verify employee cannot access Payroll Management | Security | High | Critical | FR-HR-PAY-11 | UC-HR-PAY-28 | GET /payroll | roles | Employee logged in | Access Payroll page | Access denied
TC-HR-PAY-29 | Verify only HR/Admin can run payroll | Security | High | Critical | FR-HR-PAY-11 | UC-HR-PAY-29 | POST /payroll/run | roles | Manager logged in | Attempt Run Payroll | Action blocked

## Policies
Test Report Title : WorkSphere - ELMS
Test Report Provided by : Vaheeda Sheik
Module Name : HR-POLicy Page
Designation : QA Engineer
Date : 09/02/2026
Test Case ID | Test Description | Test Type | Priority | Severity | FR ID | UC ID | API Covered | DB Tables | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID
TC-HR-POL-01 | Verify Policy Management page loads successfully | Functional | High | Major | FR-HR-POL-01 | UC-HR-POL-01 | GET /policies | policies | HR/Admin logged in | Open Policy Management page | Page loads successfully
TC-HR-POL-02 | Verify policy count displayed correctly | Functional | Medium | Minor | FR-HR-POL-02 | UC-HR-POL-02 | GET /policies/count | policies | Policies exist | View policy count | Correct count displayed
TC-HR-POL-03 | Verify policy count updates after policy creation | Integration | High | Major | FR-HR-POL-02 | UC-HR-POL-03 | GET /policies/count | policies | New policy created | Refresh page | Policy count updated
TC-HR-POL-04 | Verify Create Policy button visibility | UI | Medium | Minor | FR-HR-POL-03 | UC-HR-POL-04 | — | — | Policy page loaded | Observe Create Policy button | Button visible
TC-HR-POL-05 | Verify navigation to Create Policy page | Functional | High | Major | FR-HR-POL-03 | UC-HR-POL-05 | GET /policies/create | policies | HR/Admin logged in | Click Create Policy | Create Policy page displayed
TC-HR-POL-06 | Verify Policy Title mandatory validation | Negative | High | Major | FR-HR-POL-04 | UC-HR-POL-06 | POST /policies | policies | Create page opened | Leave title blank & submit | Validation error shown
TC-HR-POL-07 | Verify Category mandatory validation | Negative | High | Major | FR-HR-POL-04 | UC-HR-POL-07 | POST /policies | policies | Create page opened | Leave category unselected | Validation error shown
TC-HR-POL-08 | Verify Description mandatory validation | Negative | High | Major | FR-HR-POL-04 | UC-HR-POL-08 | POST /policies | policies | Create page opened | Leave description blank | Validation error shown
TC-HR-POL-09 | Verify Policy Title accepts valid input | Functional | Medium | Minor | FR-HR-POL-04 | UC-HR-POL-09 | POST /policies | policies | Create page opened | Enter valid title | Title accepted
TC-HR-POL-10 | Verify Category dropdown values | Functional | Medium | Minor | FR-HR-POL-04 | UC-HR-POL-10 | GET /policy/categories | policy_categories | Categories configured | Open Category dropdown | Categories listed
TC-HR-POL-11 | Verify file upload button visible | UI | Medium | Minor | FR-HR-POL-05 | UC-HR-POL-11 | — | — | Create page opened | Observe upload button | Upload button visible
TC-HR-POL-12 | Verify valid document upload | Functional | High | Major | FR-HR-POL-05 | UC-HR-POL-12 | POST /policies/upload | policy_documents | Valid file available | Upload document | File uploaded successfully
TC-HR-POL-13 | Verify unsupported file format validation | Negative | Medium | Minor | FR-HR-POL-05 | UC-HR-POL-13 | POST /policies/upload | policy_documents | Invalid file | Upload invalid file | Error message shown
TC-HR-POL-14 | Verify uploaded file linked to policy | DB | High | Critical | FR-HR-POL-05 | UC-HR-POL-14 | POST /policies | policy_documents | Policy created | Verify DB | File linked correctly
TC-HR-POL-15 | Verify Cancel button navigation | Functional | Medium | Minor | FR-HR-POL-06 | UC-HR-POL-15 | — | — | Create page opened | Click Cancel | Redirected to Policy list
TC-HR-POL-16 | Verify Create button creates policy | Functional | High | Major | FR-HR-POL-06 | UC-HR-POL-16 | POST /policies | policies | Mandatory fields filled | Click Create | Policy created successfully
TC-HR-POL-17 | Verify policy saved in DB | DB | High | Critical | FR-HR-POL-06 | UC-HR-POL-17 | POST /policies | policies | Policy created | Verify DB record | Record saved correctly
TC-HR-POL-18 | Verify policy list displayed | Functional | High | Major | FR-HR-POL-07 | UC-HR-POL-18 | GET /policies | policies | Policies exist | View policy list | List displayed
TC-HR-POL-19 | Verify policy title displayed correctly | Functional | Medium | Minor | FR-HR-POL-07 | UC-HR-POL-19 | GET /policies | policies | Policies exist | Check title column | Correct title shown
TC-HR-POL-20 | Verify category displayed correctly | Functional | Medium | Minor | FR-HR-POL-07 | UC-HR-POL-20 | GET /policies | policies | Policies exist | Check category | Correct category shown
TC-HR-POL-21 | Verify created date displayed | Functional | Medium | Minor | FR-HR-POL-07 | UC-HR-POL-21 | GET /policies | policies | Policies exist | Check created date | Correct date shown
TC-HR-POL-22 | Verify Draft status for unpublished policy | Functional | Medium | Minor | FR-HR-POL-08 | UC-HR-POL-22 | GET /policies | policies | Draft policy exists | View status | Status shown as Draft
TC-HR-POL-23 | Verify Publish button visible for draft policy | Functional | Medium | Minor | FR-HR-POL-08 | UC-HR-POL-23 | — | — | Draft policy exists | Observe Publish button | Button visible
TC-HR-POL-24 | Verify publish policy functionality | Functional | High | Major | FR-HR-POL-08 | UC-HR-POL-24 | PUT /policies/publish | policies | Draft policy exists | Click Publish | Policy published successfully
TC-HR-POL-25 | Verify Published status displayed | Functional | Medium | Minor | FR-HR-POL-08 | UC-HR-POL-25 | GET /policies | policies | Policy published | Refresh page | Status updated to Published
TC-HR-POL-26 | Verify View policy details | Functional | High | Major | FR-HR-POL-09 | UC-HR-POL-26 | GET /policies/{id} | policies | Policy exists | Click View | Policy details displayed
TC-HR-POL-27 | Verify Edit option visible for HR/Admin | Security | High | Major | FR-HR-POL-09 | UC-HR-POL-27 | — | roles | HR/Admin logged in | Observe Edit option | Edit option visible
TC-HR-POL-28 | Verify Edit policy updates data | Functional | High | Major | FR-HR-POL-09 | UC-HR-POL-28 | PUT /policies | policies | Policy exists | Edit and save | Policy updated successfully
TC-HR-POL-29 | Verify employee cannot edit policy | Security | High | Critical | FR-HR-POL-10 | UC-HR-POL-29 | PUT /policies | roles | Employee logged in | Attempt edit | Access denied
TC-HR-POL-30 | Verify search policy by title | Functional | Medium | Minor | FR-HR-POL-11 | UC-HR-POL-30 | GET /policies?search= | policies | Policies exist | Search by title | Matching policies displayed
TC-HR-POL-31 | Verify pagination for policy list | Functional | Medium | Minor | FR-HR-POL-11 | UC-HR-POL-31 | GET /policies?page= | policies | Multiple policies exist | Navigate pages | Correct records displayed
TC-HR-POL-32 | Verify policy publish audit log | Audit | Medium | Minor | FR-HR-POL-12 | UC-HR-POL-32 | PUT /policies/publish | audit_logs | Policy published | Verify audit log | Publish action logged

## Reports
Test HR-REPort Title : WorkSphere - ELMS
Test HR-REPort Provided by : Vaheeda Sheik
Module Name : HR-REPorts Page
Designation : QA Engineer
Date : 09/02/2026
Test Case ID | Test Description | Test Type | Priority | Severity | FR ID | UC ID | API Covered | DB Tables | Preconditions | Test Steps | Expected Result | Actual Result | Status | Defect ID
TC-HR-REP-01 | Verify Reports page loads successfully | Functional | High | Major | FR-HR-REP-01 | UC-HR-REP-01 | GET /reports | reports | HR/Admin logged in | Open Reports page | Reports page loads successfully
TC-HR-REP-02 | Verify Generate Report section is visible | UI | Medium | Minor | FR-HR-REP-01 | UC-HR-REP-02 | — | — | Reports page loaded | Observe Generate section | Generate Report section visible
TC-HR-REP-03 | Verify Report Type dropdown values | Functional | Medium | Minor | FR-HR-REP-02 | UC-HR-REP-03 | GET /reports/types | report_types | Report types configured | Open Report Type dropdown | All report types listed
TC-HR-REP-04 | Verify Period dropdown values | Functional | Medium | Minor | FR-HR-REP-02 | UC-HR-REP-04 | GET /reports/periods | — | Period options configured | Open Period dropdown | Period options displayed
TC-HR-REP-05 | Verify Report Type mandatory validation | Negative | High | Major | FR-HR-REP-02 | UC-HR-REP-05 | POST /reports/generate | reports | Generate section opened | Leave Report Type unselected | Validation error shown
TC-HR-REP-06 | Verify Period mandatory validation | Negative | High | Major | FR-HR-REP-02 | UC-HR-REP-06 | POST /reports/generate | reports | Generate section opened | Leave Period unselected | Validation error shown
TC-HR-REP-07 | Verify Export Report button visibility | UI | Medium | Minor | FR-HR-REP-02 | UC-HR-REP-07 | — | — | Generate section visible | Observe Export button | Export button visible
TC-HR-REP-08 | Verify report generation with valid inputs | Functional | High | Critical | FR-HR-REP-03 | UC-HR-REP-08 | POST /reports/generate | reports | Valid inputs selected | Click Export Report | Report generated successfully
TC-HR-REP-09 | Verify exported report file download | Functional | High | Major | FR-HR-REP-03 | UC-HR-REP-09 | GET /reports/download | reports | Report generated | Download report | File downloaded successfully
TC-HR-REP-10 | Verify exported report format (PDF/Excel) | Functional | Medium | Minor | FR-HR-REP-03 | UC-HR-REP-10 | GET /reports/download | reports | Report downloaded | Open file | Correct file format
TC-HR-REP-11 | Verify exported report data accuracy | DB | High | Critical | FR-HR-REP-03 | UC-HR-REP-11 | GET /reports/download | reports | Report downloaded | Compare with DB | Report data matches DB
TC-HR-REP-12 | Verify generated reports list displayed | Functional | High | Major | FR-HR-REP-04 | UC-HR-REP-12 | GET /reports/list | reports | Reports generated | View reports list | Generated reports listed
TC-HR-REP-13 | Verify report type displayed correctly | Functional | Medium | Minor | FR-HR-REP-04 | UC-HR-REP-13 | GET /reports/list | reports | Reports exist | Check report type | Correct report type shown
TC-HR-REP-14 | Verify View Report button visibility | UI | Medium | Minor | FR-HR-REP-04 | UC-HR-REP-14 | — | — | Reports exist | Observe View button | View button visible
TC-HR-REP-15 | Verify View Report functionality | Functional | High | Major | FR-HR-REP-04 | UC-HR-REP-15 | GET /reports/{id} | reports | Report exists | Click View Report | Report opened successfully
TC-HR-REP-16 | Verify no data message for empty report | Negative | Medium | Minor | FR-HR-REP-05 | UC-HR-REP-16 | POST /reports/generate | reports | No data for period | Generate report | No data message shown
TC-HR-REP-17 | Verify large date range performance | Performance | Medium | Minor | FR-HR-REP-05 | UC-HR-REP-17 | POST /reports/generate | reports | Large data exists | Generate report | Report generated within time
TC-HR-REP-18 | Verify multiple report generation handling | Integration | Medium | Minor | FR-HR-REP-05 | UC-HR-REP-18 | POST /reports/generate | reports | Reports exist | Generate multiple reports | All reports listed correctly
TC-HR-REP-19 | Verify employee cannot access Reports page | Security | High | Critical | FR-HR-REP-06 | UC-HR-REP-19 | GET /reports | roles | Employee logged in | Access Reports page | Access denied
TC-HR-REP-20 | Verify report generation audit log | Audit | Medium | Minor | FR-HR-REP-07 | UC-HR-REP-20 | POST /reports/generate | audit_logs | Report generated | Verify audit entry | Action logged correctly